## Sheet1
PROJECT CHARTER
Project Title | Charcha - Strengthening Communication |  |  | Project Manager | Dr Jafar Hamra
Project Start Date | 2021-03-12 | Project End Date | 21-05-2021 | Project Sponsor | CM Kamal & SB Mahesh
Description
Charcha is a service that has support for everyone to communicate smoothly. It is a service enabling effective communication of hearing and speech impaired among themselves and also with other people. It achieves this by live sign language to text transcription powered by robust Convolutional Neural Networks and Computer Vision techniques.
Project Scope |  |  | Deliverables
The ASL sign language is a mixture of hand gestures, lip movement, expressions and sequential hand movements. The coherent use of all 4 components enables a deaf, mute or blind person to communicate with others. Considering the complexity of the problem, our project will be limited to interpretation of signs in the forms of text. This will help a gifted person to communicate with other gifted people and with masses that do not understand the dynamics of ASL. |  |  | > Service to convert hand signs & gestures to text > Desktop App > Self curated Dataset
Risks & Issues |  |  | Assumption/Dependencies
> Creation of a robust GUI can be difficult due to lack of experience in web/software development |  |  | > Conversion of only one single language - ASL > Although the dataset would be extremely comprehensive and inclusive of some of the most difficult image interpretation instances, we have to be assuming that there could be edge cases where the model could look forward to improvements in judgement
Financials
Time = [8 hrs (Discussion & Planning) + 4 hrs (Execution)] /per week Money = $ 0
Milestones Schedule
Milestone |  | Target Completion Date |  | Actual Date
Dataset Creation |  | 31-03-2021 |  | 31-03-2021
Data Conformation & Model Creation |  | 2021-04-25 |  | 2021-04-25
Coding & Implementation of app with GUI |  | 2021-05-07 |  | 2021-05-05
Documentation & Final Report Making |  | 2021-05-20 |  | 20-05-2021
Final Presentation |  | 2021-05-21 |  | 2021-05-21
Project Team |  |  | Approval/Review Committee
Team Member | Gautam Sadarangani |  | Sponsor | CM Kamal & SB Mahesh
Team Member | Pratiksha Sharma |  | Stakeholder | Dr Jafar Hamra, CM Kamal & SB Mahesh
Team Member | Rithwik Chhugani |  | Financial Head | Pratiksha Sharma