## Sheet1
Activity | Start Date | End Date | Duration | Status | time axis 2021-03-12 to 2021-05-21
Research and understanding of existing solutions | 2021-03-12 | 2021-03-18 | 7 | Completed | 2021-03-12: Completed; 2021-03-13: Completed; 2021-03-14: Completed; 2021-03-15: Completed; 2021-03-16: Completed; 2021-03-17: Completed; 2021-03-18: Completed
Discussion of Proprietorship, Copyright and T&C | 2021-03-15 | 2021-03-17 | 3 | Completed | 2021-03-15: Completed; 2021-03-16: Completed; 2021-03-17: Completed
Dataset Creation: Collection | 2021-03-19 | 2021-03-28 | 10 | Completed | 2021-03-19: Completed; 2021-03-20: Completed; 2021-03-21: Completed; 2021-03-22: Completed; 2021-03-23: Completed; 2021-03-24: Completed; 2021-03-25: Completed; 2021-03-26: Completed; 2021-03-27: Completed; 2021-03-28: Completed
Dataset Creation: Creation of Charcha talks Google Drive | 2021-03-21 | 2021-03-21 | 1 | Completed | 2021-03-21: Completed
Dataset Creation: Enabling Charcha Talks Google Drive access to all team members and sponsors | 2021-03-21 | 2021-03-23 | 3 | Completed | 2021-03-21: Completed; 2021-03-22: Completed; 2021-03-23: Completed
Dataset Creation: Data Transfer to Shared Drive | 2021-03-28 | 2021-03-31 | 4 | Completed | 2021-03-28: Completed; 2021-03-29: Completed; 2021-03-30: Completed; 2021-03-31: Completed
Data Conformation | 2021-04-01 | 2021-04-01 | 1 | Completed | 2021-04-01: Completed
Model Architecture Option Creations | 2021-04-02 | 2021-04-06 | 5 | Completed | 2021-04-02: Completed; 2021-04-03: Completed; 2021-04-04: Completed; 2021-04-05: Completed; 2021-04-06: Completed
Training multiple models | 2021-04-06 | 2021-04-21 | 16 | Completed | 2021-04-06: Completed; 2021-04-07: Completed; 2021-04-08: Completed; 2021-04-09: Completed; 2021-04-10: Completed; 2021-04-11: Completed; 2021-04-12: Completed; 2021-04-13: Completed; 2021-04-14: Completed; 2021-04-15: Completed; 2021-04-16: Completed; 2021-04-17: Completed; 2021-04-18: Completed; 2021-04-19: Completed; 2021-04-20: Completed; 2021-04-21: Completed
Testing and Tweaking models | 2021-04-08 | 2021-04-21 | 14 | Completed | 2021-04-08: Completed; 2021-04-09: Completed; 2021-04-10: Completed; 2021-04-11: Completed; 2021-04-12: Completed; 2021-04-13: Completed; 2021-04-14: Completed; 2021-04-15: Completed; 2021-04-16: Completed; 2021-04-17: Completed; 2021-04-18: Completed; 2021-04-19: Completed; 2021-04-20: Completed; 2021-04-21: Completed
Applying filters on Data: Gaussian Blur | 2021-04-17 | 2021-04-17 | 1 | Completed | 2021-04-17: Completed
Researching and Trying application formats and tools | 2021-04-22 | 2021-04-26 | 5 | Completed | 2021-04-22: Completed; 2021-04-23: Completed; 2021-04-24: Completed; 2021-04-25: Completed; 2021-04-26: Completed
Finalising a model with sponsors | 2021-04-24 | 2021-04-25 | 2 | Completed | 2021-04-24: Completed; 2021-04-25: Completed
Finalising Format (Desktop App) & GUI | 2021-04-27 | 2021-04-28 | 2 | Completed | 2021-04-27: Completed; 2021-04-28: Completed
Coding for the application with the GUI | 2021-04-29 | 2021-05-05 | 7 | Completed | 2021-04-29: Completed; 2021-04-30: Completed; 2021-05-01: Completed; 2021-05-02: Completed; 2021-05-03: Completed; 2021-05-04: Completed; 2021-05-05: Completed
Documentation & Final Report Making | 2021-05-06 | 2021-05-20 | 15 | Completed | 2021-05-06: Completed; 2021-05-07: Completed; 2021-05-08: Completed; 2021-05-09: Completed; 2021-05-10: Completed; 2021-05-11: Completed; 2021-05-12: Completed; 2021-05-13: Completed; 2021-05-14: Completed; 2021-05-15: Completed; 2021-05-16: Completed; 2021-05-17: Completed; 2021-05-18: Completed; 2021-05-19: Completed; 2021-05-20: Completed
Final Presentation | 2021-05-21 | 2021-05-21 | 1 | Completed | 2021-05-21: Completed
Formulas:
End Date = [Start Date]+[Duration]-1