## Sheet1
Network Diagram
Activity | Index Number | Start Date | End Date | Duration | Status
Research and understanding of existing solutions | 1 | 2021-03-12 | 2021-03-18 | 7 | Completed
Discussion of Proprietorship, Copyright and T&C | 2 | 2021-03-15 | 2021-03-17 | 3 | Completed
Dataset Creation: Collection | 3 | 2021-03-19 | 2021-03-28 | 10 | Completed
Dataset Creation: Creation of Charcha talks Google Drive | 4 | 2021-03-21 | 2021-03-21 | 1 | Completed
Dataset Creation: Enabling Charcha Talks Google Drive access to all team members and sponsors | 5 | 2021-03-21 | 2021-03-23 | 3 | Completed
Dataset Creation: Data Transfer to Shared Drive | 6 | 2021-03-28 | 2021-03-31 | 4 | Completed
Data Conformation | 7 | 2021-04-01 | 2021-04-01 | 1 | Completed
Model Architecture Option Creations | 8 | 2021-04-02 | 2021-04-06 | 5 | Completed
Training multiple models | 9 | 2021-04-06 | 2021-04-21 | 16 | Completed
Testing and Tweaking models | 10 | 2021-04-08 | 2021-04-21 | 14 | Completed
Applying filters on Data: Gaussian Blur | 11 | 2021-04-17 | 2021-04-17 | 1 | Completed
Researching and Trying application formats and tools | 12 | 2021-04-22 | 2021-04-26 | 5 | Completed
Finalising a model with sponsors | 13 | 2021-04-24 | 2021-04-25 | 2 | Completed
Finalising Format (Desktop App) & GUI | 14 | 2021-04-27 | 2021-04-28 | 2 | Completed
Coding for the application with the GUI | 15 | 2021-04-29 | 2021-05-05 | 7 | Completed
Documentation & Final Report Making | 16 | 2021-05-06 | 2021-05-20 | 15 | Completed
Final Presentation | 17 | 2021-05-21 | 2021-05-21 | 1 | Completed
Formulas:
End Date = [Start Date]+[Duration]-1

## Sheet2
Nodes |  |  |  | Network Diagram
Start Date | End Date | 2021-03-12 | 2021-03-18
Index |  | 1
Status | Duration | Completed | 7
2021-03-15 | 2021-03-17 | 2021-03-19 | 2021-03-28
2 |  | 3
Completed | 3 | Completed | 10
2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-03-23
4 |  | 5
Completed | 1 | Completed | 3
2021-03-28 | 2021-03-31 | 2021-04-01 | 2021-04-01
6 |  | 7
Completed | 4 | Completed | 1
2021-04-02 | 2021-04-06 | 2021-04-06 | 2021-04-21
8 |  | 9
Completed | 5 | Completed | 16
2021-04-08 | 2021-04-21 | 2021-04-17 | 2021-04-17
10 |  | 11
Completed | 14 | Completed | 1
2021-04-22 | 2021-04-26 | 2021-04-24 | 2021-04-25
12 |  | 13
Completed | 5 | Completed | 2
2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-05-05
14 |  | 15
Completed | 2 | Completed | 7
2021-05-06 | 2021-05-20 | 2021-05-21 | 2021-05-21
16 |  | 17
Completed | 15 | Completed | 1