## Sheet1
Stakeholder Register
Project Manager | Jafar Hamra |  |  | Project Phase |  | Completed
Name of Stakeholder | Role | Contact | Category | Interest | Influence | Expectations | Comms Requirements
C M Kamal | Project Sponsor | Phone: +919879372322 | External | High | High | User friendly application that works seamlessly and is able to succesfully fulfill the requirements. | Video Conference and Phone
S B Mahesh | Project Sponsor | Phone: +919820214142 | External | High | High | An application that is able to help the people with hearing and vocal impairment. | Video Conference and Phone
Rithwik Chhugani | Team Member | Email: rithwik.bs18bds008@spjain.org | Internal | High | High | Fulfilling the expectations of project managers and sponsors by building a robust and seamless app. | Video Conference and Email
Pratiksha Sharma | Team Member | Email: pratiksha.bs18bds010@spjain.org | Internal | High | High | Learning more about applyying CNN in real life scenario. Delivering a product that benefits the society. | Video Conference and Email
Gautam Sadarangani | Team Member | Email: gautam.bs18bds015@spjain.org | Internal | High | High | Building a product that can help people as well as enhance my learning. Gaining experience from a real-life project and understanding the work process behind it. | Video Conference and Email
Jafar Hamra | Project Manager | Email: jafar.hamra@yahoo.com | Internal | High | High | Understanding the software development process from beginning to end. Successful delivery of a working product. | Email
Customers | Users | - | External | High | - | A working product which would help reduce the communication barriers between people with hearing and speaking impairment. | -